## Sheet1
Team | Task | Assigned | Remarks | Status
DEV | Floating Menu on all pages. | NA |  | Completed
DEV | Large Floating Menu Icon | NA | Give 8px from bottom | InProgress
DEV | Remove address field while creating Mandir | NA |  | Completed
DEV | Notifications - Daily (Calendar for 365) - Keep in a table | NA |  | InProgress
Dev | Create 365 Days Calender place holder - To send notification for all users | NA | 6:30am Daily send to all users | Pending
DEV | Mangal Mart - Floating Menu & add Buy Link | NA |  | Completed
DEV | Mandli/Association/Society of religious block | NA |  | New Module
BDE | Social media paid add 5k per month : Ranjit | RS | Advt Image - HJ will give today | OnProgress
BDE | Invitations Letter printout for Pandit | HJ |  | Completed
BDE | Design QR to paste in front of Mandir | HJ |  | Completed
BDE | List of Influcers - 200 Invitation Printed/Digital | HJ |  | Pending
BDE | Purchase two SIM for Mangal Bhav for Whatsapp & calling | HJ |  | Completed
BDE | Find field boys who can paste QR on Mandir & Create Mandir in App | HJ |  | Pending
BDE | Provide purchase link for Amazon & FlipKart | RS |  | Completed
BDE | Test Case document for 20 - Excel sheet to test mobile app | HJ | Upload test case document in google sheet | Pending